## DEPLOYMENT PLAN
PM Regulatory Returns Rendition Monitoring System DEPLOYMENT CHECK-LIST
Task | Start date | Finish date | Owner | Status | Comments/progress
Back-Up of Current Bulids | Saturday 14th, Jan, 2023 | Saturday 14th, Jan, 2023 | APPSUPPORT | Scheduled
Export process and tables from PM test environment (192.168.250.16) | Saturday 14th, Jan, 2023 | Saturday 14th, Jan, 2023 | APPSUPPORT | Scheduled
Deploy 3RMS periodic rendition process to Production (192.168.0.114) | Saturday 14th, Jan, 2023 | Saturday 14th, Jan, 2023 | APPSUPPORT | Scheduled
Restart-Up Services | Saturday 14th, Jan, 2023 | Saturday 14th, Jan, 2023 | APPSUPPORT | Scheduled
Review and Monitor | Saturday 14th, Jan, 2023 | Saturday 14th, Jan, 2023 | APPSUPPORT | Scheduled